## Notes
CL#12-2683

## Final
KNOWLEDGE NEEDED | [5 empty] | IMPLEMENTATION PATH | [5 empty] | TIMING |  | Comments | Science objectives that can be address in synergy with this investigation
SKG # | SKG | SKG Nickname | Gap filling activity | Investigations | Purpose/ rationale | Measurements and demonstrations | Priority | Location | How to turn measurements into needed knowledge | Potential instruments | Instrument Readiness | Duration | When needed | Comments
A1 | A1. Upper Atmosphere. The current Martian atmospheric observations (density, pressure, temperature, aerosols and dynamics) have significant limitations for supporting aerocapture and aerobraking design, especially for human-scale missions. | A1. Upper Atmosphere. | A1-1. Global temperature field. | Objective: Reduce uncertainty in atmospheric temperature to improve confidence in the tails (>99% level) through observations of the global atmospheric temperature field (both the climatology and the weather variability). Full diurnal coverage is especially lacking so that any time of day can be selected for aerocapture, landing or launch. | Rationale: Provides density for aerocapture, EDL, and ascent profiles, provides validation data for global atmosphere models | Measurement Type: Global Temperature Field Precision/Coverage: ≤5 km vertical, ≤10 km horizontal, global, at all local times, from 20 km to > 80 km | 1. High | Mars Orbit | The temperature field is used to improve the models by insuring the model can meet the range of conditions see in the real atmosphere. It is directly combined with the models in data assimilation. This feeds into A2. | Mid IR limb and nadir sounding with radiometer or spectrometer; other techniques are also available (e.g., microwave radiometer) | Previously flown technology: MCS, TES, instrument in development for Trace Gas Orbiter | >5 Martian years | 1. IV- | Needed in non-sun synchronous orbit for local time coverage.
A1 | A1. Upper Atmosphere. The current Martian atmospheric observations (density, pressure, temperature, aerosols and dynamics) have significant limitations for supporting aerocapture and aerobraking design, especially for human-scale missions. | A1. Upper Atmosphere. | A1-2. Global aerosol profiles and properties | Objective: To understand and model the performance of guidance and control systems (particularly pinpoint landing sensors). | Rationale: The aerosols are an important driver of the atmospheric state, so they are critical for the atmospheric modeling accuracy. | Measurement Type: Aerosol Profiles and properties, including optical properties, particle sizes, and number densities, from surface to >60 km Precision/Coverage: <5 km vertical resolution, global coverage, including all local times | 1. High | Mars Orbit | The aerosol field is used to improve the models by providing the thermodynamical driver for a given atmospheric state the model is attempting to reproduce. It is directly combined with the models in data assimilation. This feeds into A2. | Visible plus mid-IR limb sounding provides the aerosol composition, profiles and particle sizes, radiometer/bolometer or spectrometer, multi-wavelength Lidar | Remote sounding portion is previously flown technology (MCS), instrument in development for TGO | >5 Martian years | 1. IV- | MSL aeroshell is instrumented
A1 | A1. Upper Atmosphere. The current Martian atmospheric observations (density, pressure, temperature, aerosols and dynamics) have significant limitations for supporting aerocapture and aerobraking design, especially for human-scale missions. | A1. Upper Atmosphere. | A1-3. Global winds and wind profiles | Objective: Characterize Winds (important for model validation as well as pinpoint landing) | Rationale: Validate models | Measurement Type: Global coverage (above 15 km) of wind velocity and direction Precision/Coverage: global distribution; precision of 2-3 m/s, for both horizontal components, vertical resolution of 5 km. TES/MCS-like horizontal resolution and spacing in longitude and time | 2. Medium | Mars Orbit | The wind field is used to improve the models by insuring the model can meet the range of conditions seen in the real atmosphere. It is directly combined with the models in data assimilation. | Lidar, microwave, others TBD | Near-flight units in ground testbeds. [3-5] years to readiness for Mars. | >5 Martian years | 1. IV-
A2 | A2. Atmospheric Modeling. The atmospheric models for Mars have not been well validated due to a lack of sufficient observational data, and thus our confidence in them (for use in mission engineering) is significantly limited. | A2. Atmospheric Modeling. | A2-1. Atm. Modeling. | Validation of Mars atmospheric models related to EDL. | This allows the models to be confidently used to create the extreme conditions (>99% distribution tail) necessary to select and design aerocapture, EDL, aerobraking and launch systems. | There are 4 types of models to improve: MGCM (Mars General Circulation Models) provide global temperature and wind fields from the surface to aerobraking altitudes Mesoscale models provide local and regional weather and climate conditions that account for the local topography. LES (Large Eddy Simulations) provide the small-scale local conditions (such as dust devils) that are superimposed on the regional weather. Data Assimilation quantitatively combines observations and model fields to produce a model output (reanalysis) containing the weather from the measurements and complete set of atmospheric fields from the model. | 1. High | Earth | The models are improved by comparing the results to the observations to determine where the physics is deficient and/or the variable parameters are incorrect. The data also provides the range of initial/possible conditions that the models need to be able to reproduce. Once the models are tuned, multiple runs are performed with varying initial and boundary conditions to create possible extreme events under different types of conditions. | Earth based investigations | N/A | Model developments and improvements will take up to a (terrestrial) decade, but can be started as significant "blocks" of the needed measurements become available. | 1. IV- | Orbiter with high-Mars orbit, or elliptical orbit that has both low- and high- aspects
A3 | A3. Orbital Particulates. We have insufficient information about the orbital particulate environment in high-Mars orbit that may impact the delivery of cargo and crew to the Martian system. | A3. Orbital Particulates. | A3-1. Orbital particulate environment | Particulate environment near Phobos and Deimos (especially in and around the equatorial plane of Mars) | Particulates are potential hazards to spacecraft on approach to Mars, into orbit around Mars, and especially in proximity to Phobos and Deimos. | Spatial variation in size-frequency distribution of Phobos/Deimos ejecta particles in Mars orbit | 2. Medium | Mars Orbit | Specifically there maybe a dust ring between Phobos and Deimos located in and around the equatorial plane of Mars. Knowledge of the presence of these particulates, and their size frequency distribution will help mission architecture planning and engineering designs for cargo and human missions to Mars orbit. This would feed into A4. | Orbital particulate detector, imaging system | Previously flown technology | A single precursor mission could provide enough information on the orbital particulate environment. | 1. IV- | Debris. Orbital particulate environment potentially more significant in high Mars orbit (near Phobos/Deimos) than in low Mars orbit. There is some evidence to suggest that orbital particulates may be prevalent in high Mars orbit. | Related to impact histories, regolith and particulate dynamics and the evolution of small bodies. Of interest to SBAG science objectives see SBAG roadmap.
A4 | A4. Technology: To/from Mars System. In addition to the specific challenges listed above, we do not have the required technology available to: (1) sustain human life during long duration flight to/from Mars and around Mars; (2) launch and return human-scale payloads to/from Mars orbit. | A4. Technology: To/from Mars System. | A4-1. Autonomous rendezvous and docking demo | Demonstrate Automated/Autonomous rendezvous & docking, proximity operations, target relative navigation |  | Demonstration could be in Earth orbit or Mars orbit | 1. High | Earth or Mars Orbit |  | Technology demo | New technology | Single demonstration sufficient | 1. IV- | MSR would demonstrate.
A4 | A4. Technology: To/from Mars System. In addition to the specific challenges listed above, we do not have the required technology available to: (1) sustain human life during long duration flight to/from Mars and around Mars; (2) launch and return human-scale payloads to/from Mars orbit. | A4. Technology: To/from Mars System. | A4-2. Optical Comm. Tech demo | Demonstrate Laser optical communication | Demonstrate the ability to support the high rate communications to/from Mars needed to support the crew in the Martian system | Demonstration could be on Earth, in Earth orbit, or in Mars orbit | 1. High | Earth or Mars Orbit |  | Technology demo | New technology | Single demonstration sufficient | 1. IV- | good compliment to HiRISE class imaging
A4 | A4. Technology: To/from Mars System. In addition to the specific challenges listed above, we do not have the required technology available to: (1) sustain human life during long duration flight to/from Mars and around Mars; (2) launch and return human-scale payloads to/from Mars orbit. | A4. Technology: To/from Mars System. | A4-3. Aerocapture demo | Demonstrate Aerocapture | Aerocapture is a potential architecture choice for getting to Mars orbit, providing significant saving in mass sent to the martian system | Demonstration could be on Earth, in Earth orbit, or in Mars orbit | 2. Medium | Earth or Mars Orbit |  | Technology demo | New technology | Single demonstration sufficient | 1. IV- | could test pinpoint landing on MSR, SRL mission
A4 | A4. Technology: To/from Mars System. In addition to the specific challenges listed above, we do not have the required technology available to: (1) sustain human life during long duration flight to/from Mars and around Mars; (2) launch and return human-scale payloads to/from Mars orbit. | A4. Technology: To/from Mars System. | A4-4. Auto systems tech demo | Demonstrate autonomous vehicle systems management |  | Demonstration could be on Earth or in Earth orbit | 3. Low | Earth |  | Earth based investigations | New technology | Single demonstration sufficient | 1. IV-
A4 | A4. Technology: To/from Mars System. In addition to the specific challenges listed above, we do not have the required technology available to: (1) sustain human life during long duration flight to/from Mars and around Mars; (2) launch and return human-scale payloads to/from Mars orbit. | A4. Technology: To/from Mars System. | A4-5. In space prop tech demo | Demonstrate advanced in-space propulsion systems |  | Demonstration could be on Earth or in Earth orbit | 1. High | Earth |  | Earth based investigations | New technology | Single demonstration sufficient | 1. IV-
A4 | A4. Technology: To/from Mars System. In addition to the specific challenges listed above, we do not have the required technology available to: (1) sustain human life during long duration flight to/from Mars and around Mars; (2) launch and return human-scale payloads to/from Mars orbit. | A4. Technology: To/from Mars System. | A4-6. Life support tech demo | Demonstrate life support and environmental monitoring technologies needed to get the crew to and from Mars | Need life support for crew to survive the trip | Demonstration could be on Earth or in Earth orbit | 1. High | Earth |  | Earth based investigations | New technology | Single demonstration sufficient | 1. IV-
A4 | A4. Technology: To/from Mars System. In addition to the specific challenges listed above, we do not have the required technology available to: (1) sustain human life during long duration flight to/from Mars and around Mars; (2) launch and return human-scale payloads to/from Mars orbit. | A4. Technology: To/from Mars System. | A4-7. Mechanisms tech demo | Demonstrate mechanisms for long duration, deep space missions | Must have mechanisms that work in space throughout long duration human missions | Demonstration could be on Earth or in Earth orbit | 3. Low | Earth |  | Earth based investigations | New technology | Single demonstration sufficient | 1. IV-
B1 | B1. Lower Atmosphere. We do not have sufficient martian atmospheric observations to confidently model winds, which significantly affect EDL design, or atmospheric electricity, in the forms of electric fields and conductivity, to understand the risks to ascent vehicles, ground systems, and human explorers. | B1. Lower Atmosphere. | B1-1. Dust Climatology | Objective: To understand the statistics of dust events. | Rationale: To better define human architecture requirements related to whether it is feasible to "wait out” a dust storm | Measurement Type: Dust and aerosol activity climatology Other Considerations: These observations are needed simultaneously with all other observation types. | 1. High | Mars Orbit | The occurrence, size and duration of dust storms is not uniform on Mars. These measurements will provide the statistical information to estimate the probability severity and length of possible events. | Visible low resolution wide angle camera | Previously flown technology: MARCI on MRO, MOC-WA on MGS; instrument in development for TGO | >10 Martian years | 4. IV Late | This data provides the amount of time the astronauts need to be able to wait in orbit before landing or wait on the surface before launching.
B1 | B1. Lower Atmosphere. We do not have sufficient martian atmospheric observations to confidently model winds, which significantly affect EDL design, or atmospheric electricity, in the forms of electric fields and conductivity, to understand the risks to ascent vehicles, ground systems, and human explorers. | B1. Lower Atmosphere. | B1-2. Global surface pressure; local weather | Objective: To validate global model extrapolations of surface pressure | Rationale: Provides density for EDL and ascent profiles, provides validation data for global atmosphere models | Measurement Type: Surface Pressure; Precision/Coverage: Full diurnal cycle, Sampling rate > 0.01 Hz and a precision of 10-2 Pa Lander measurements simultaneous with temperature and dust from orbit, from multiple locations for multiple Martian years. Other Considerations: The pressure is needed at all local weather stations | 1. High | Mars surface | Surface pressure is a measure of the total atmospheric column that will be experienced during EDL. It is also use to make sure numerical models provide the proper boundary conditions for EDL. | Pressure sensors (multiple mature technology options), ideally on a network of long-lived ground stations | Previously flown technology: ASI/MET on MPF and MET on PHX | for multiple Martian years. | 3. IV Early
B1 | B1. Lower Atmosphere. We do not have sufficient martian atmospheric observations to confidently model winds, which significantly affect EDL design, or atmospheric electricity, in the forms of electric fields and conductivity, to understand the risks to ascent vehicles, ground systems, and human explorers. | B1. Lower Atmosphere. | B1-2. Global surface pressure; local weather | Objective: To validate regional and local model atmospheric conditions | Rationale: Provides local surface and near surface validation data for mesoscale and LES models | Measurement Type: Surface meteorological packages (including T, surface winds, relative humidity, aerosol column), Upward-looking remote sounder for high vertical resolution T and aerosol profiles below ~10 km Precision/Coverage: Full diurnal cycle, sampling rate > 0.01 Hz Lander measurements simultaneous with temperature and dust from orbit. | 1. High | Mars surface | Surface meteorology conditions bound the conditions expected during the last stages of descent and is used to validate the high resolution models of the lower atmosphere, especially the boundary layer. Feeds into A2 (especially mesoscale and LES models). | Surface meteorological package | Previously flown technology: ASI/MET on MPF, mini-TES on MER and MET+LIDAR on PHX | for multiple Martian years. | 3. IV Early | All landers and rovers should have a meteorology package to sample a wide variety of conditions. This is especially important for long lasting rovers and landers.
B1 | B1. Lower Atmosphere. We do not have sufficient martian atmospheric observations to confidently model winds, which significantly affect EDL design, or atmospheric electricity, in the forms of electric fields and conductivity, to understand the risks to ascent vehicles, ground systems, and human explorers. | B1. Lower Atmosphere. | B1-2. Global surface pressure; local weather | Objective: Local Weather at multiple sites, including human landing site Rationale: To validate model boundary schemes | Objective: Local Weather at multiple sites, including human landing site Rationale: To validate model boundary schemes | Surface meteorological packages (including T, surface winds, relative humidity), upward-looking remote sounder for high vertical resolution T and aerosol profiles below ~10 km Plus Upward looking temperature, aerosol profiles Measurement Location/Duration: below 10 km, high vertical resolution [TBD], full diurnal cycle Lidar, sun tracking visible (near UV/IR) filters, camera (or bolometer?), upward pointing mid-IR radiometer or spectrometer" | 1. High | Mars surface |  | Surface meteorological package Upward looking LIDAR Pancam with sun tracking filters upward looking IR sounder | Previously flown technology, but improvements probably needed [TBD] | for multiple Martian years. | 4. IV Late
B1 | B1. Lower Atmosphere. We do not have sufficient martian atmospheric observations to confidently model winds, which significantly affect EDL design, or atmospheric electricity, in the forms of electric fields and conductivity, to understand the risks to ascent vehicles, ground systems, and human explorers. | B1. Lower Atmosphere. | B1-3. Surface winds | Objective: Characterize Winds (important for model validation as well as pinpoint landing) | Rationale: Reduces uncertainties and system masses for EDL, precision landing, shedding of components during EDL | Measurement Type: Vertical Profiling at Lower Levels (0-15 km) Precision/Coverage: 1 to 5 vertical levels in representative regions (plains, up/down wind of topography, canyons); precision of 2 m/s, for horizontal components; resolution 1 km vertical, 100 m horizontal. In years with and without a major dust storm: hourly profiling, continuous daily observations Other Considerations: Would like to measure vertical winds in the planetary boundary layer (PBL); these get large in strongly convective mixed layers; would like to measure the turbulent winds in the daytime PBL; requires high frequency sounding; simultaneity with global wind and temperature and aerosol measurements made from orbit; simultaneity with very near-surface wind measurements made by landers/rovers at the same location, cloud tracking by moderate and high resolution imaging from orbit | 2. Medium | Mars surface | Lower atmosphere winds are used to insure that high resolution models are capable of generating profiles matching those seen at Mars. Dust storms. | Surface Atmospheric LIDAR for winds | [3-5] years to readiness for Mars. | >5 Martian years | 3. IV Early
B1 | B1. Lower Atmosphere. We do not have sufficient martian atmospheric observations to confidently model winds, which significantly affect EDL design, or atmospheric electricity, in the forms of electric fields and conductivity, to understand the risks to ascent vehicles, ground systems, and human explorers. | B1. Lower Atmosphere. | B1-4. EDL profiles | Objective: Reduce uncertainty in atmospheric temperature to improve confidence in the tails (>99% level) through observations of vertical temperature profiles | Rationale: Provides density for EDL and ascent profiles, provides validation data for global atmosphere models | Measurement Type: High Vertical Resolution Temperature Profiles Precision/Coverage: ≤1 km vertical, global, at several local times, from ground to 20 km | 2. Medium | Mars EDL | The temperature profile is a measure of the density profile (through the ideal gas law and hydrostatic equation). It is used to insure that high resolution models are capable of generating profiles matching those seen at Mars. This feeds into A2. | Instrumented EDL/flight systems, Earth radio occultation, multi-orbiter mutual occultations ("GPS") | Previously flown technology (instrumented MPF, PHX, and MER EDLs; MGS and MRO Earth radio occultation); orbiter mutual occultations used for terrestrial missions | As many as possible (instrument every EDL system) | 3. IV Early | MSL aeroshell is instrumented
B1 | B1. Lower Atmosphere. We do not have sufficient martian atmospheric observations to confidently model winds, which significantly affect EDL design, or atmospheric electricity, in the forms of electric fields and conductivity, to understand the risks to ascent vehicles, ground systems, and human explorers. | B1. Lower Atmosphere. | B1-5. Atmospheric Electricity conditions | Electrical properties of the Martian environment | Assess communications interference, and determine location, intensity, and relevant conditions for discharge events Assess electrical hazards associated with Mars Take-off, Ascent, and Orbit-Insertion (MTAO) Determine role of surface in charge dissipation and grounding Determine hazards associated with charged dust Determine role of atmosphere in creating or mitigating electrical charge buildup; assess discharge hazards | AC electric fields from the surface to < 50 km; 10 uV/m - 10 V/m, 10 Hz-200 MHz with as much as 20 Hz bandwidth resolution and intermittent waveform capture Quasi-static DC electric fields at the surface and at low altitude (<10 km); 5 V/m - 80 kV/m with 10% resolution, from DC-10 Hz Ground electrical conductivity from surface to <10 km; >1E-13 S/m Dust grain charge from surface, low altitude balloon or airplane (<10 km); >1E-17 C for grains 1-100 um radius Atmospheric electrical conductivity from the surface to < 10 km; 1E-15 to 1E-10 S/m with 10% resolution | 3. Low | Mars surface |  | AC radio receivers DC electric field meters (double-probes, field mills, electrometers) Direct conductivity probes (i.e., Phoenix) or use AC radio receivers above at <10 km Dust detectors (induction tubes, grids, impact plates) Relaxation probe, Gerdien condensers | Some instruments previously flown (TRL 8-9). Others at TRL 6 or above | Periodically throughout one martian year (encompassing one dust storm season) | 4. IV Late
B1 | B1. Lower Atmosphere. We do not have sufficient martian atmospheric observations to confidently model winds, which significantly affect EDL design, or atmospheric electricity, in the forms of electric fields and conductivity, to understand the risks to ascent vehicles, ground systems, and human explorers. | B1. Lower Atmosphere. | B1-6. EDL demo | Demonstrate EDL at the scale needed to support human exploration | Must be able to land payloads of crew, habitats and other systems on the Martian surface. | Demonstration could be on Earth or in Earth orbit | 1. High | Mars EDL |  | Technology demo | New technology | Single demonstration sufficient | 3. IV Early
B1 | B1. Lower Atmosphere. We do not have sufficient martian atmospheric observations to confidently model winds, which significantly affect EDL design, or atmospheric electricity, in the forms of electric fields and conductivity, to understand the risks to ascent vehicles, ground systems, and human explorers. | B1. Lower Atmosphere. | B1-7. Ascent demo | Demonstrate planetary ascent vehicles | Must be able to return the crew from the martian surface | Demonstration could be on Earth or on the Martian surface | 1. High | Earth or Mars Surface |  | Technology demo | New technology | Single demonstration sufficient | 3. IV Early | MSR would demonstrate.
B2. | B2. Back Contamination to Earth. We do not know whether the Martian environments to be contacted by humans are free, to within acceptable risk standards, of biohazards that might have adverse effects on some aspect of the Earth's biosphere if uncontained Martian material were returned to Earth. | B2. Back Contamination to Earth. | B2-1. Biohazards | Determine if there are biohazards | 1B. Determine if the Martian environments to be contacted by humans are free, to within acceptable risk standards, of biohazards that might have adverse effects on the crew that might be directly exposed while on Mars, and on other terrestrial species if uncontained Martian material would be returned to Earth. Note that determining that a landing site and associated operational scenario would be sufficiently safe is not the same as proving that life does not exist anywhere on Mars. | Requires returned samples, allowing use of the full analytical capabilities of terrestrial laboratories and an analytical approach that could be both comprehensive and adaptive, with the analytical strategy changing as more is learned about Mars through the returned samples. | 1. High | Sample return | Despite the best intentions and best engineering it is likely that some uncontained martian dust and regolith will be returned to Earth with the crew. The safest and possible the only acceptable way to ensure non-release of biohazardous material is to return carefully contained samples to Earth prior to the first human mission. Prior to that mission, one or more diverse sets of regolith, rock and dust samples should be collected from sites representative of the diversity anticipated at human landing sites and returned to Earth for comprehensive biohazard testing similar to that outlined in Rummel et al., (2002) to determine whether any indigenous life is present and, if so, whether it presents a hazard to the Earth’s biosphere. | Returned sample analysis | Significant new technology needed. | Likely to take many years for the investigations to yield acceptable results. | 3. IV Early | May require an MSR to the human landing site.
B3 | B3. Crew Health & Performance. We do not understand in sufficient detail the factors affecting crew health and performance, specifically including the biological effects of the radiation environment at the martian surface and the potential toxic properties of the martian dust. | B3. Crew Health & Performance | B3-1. Neutrons with directionality | Neutrons | Determine potential hazards to the crew due to radiation. Neutrons can be highly biologically effective and therefore contribute a significant share of the dose equivalent. | Measure neutrons with directionality from <10 keV to >100 MeV (The MSL RAD measures neutrons with > a few MeV, but no directionality) | 2. Medium | Mars surface |  | Radiation detector suite | Previously flown technology | Periodically throughout one martian year (through an entire solar cycle desired)). Solar minimum measurements most desirable. | 4. IV Late | Neutrons can be highly biologically effective and therefore contribute a significant share of the dose equivalent.
B3 | B3. Crew Health & Performance. We do not understand in sufficient detail the factors affecting crew health and performance, specifically including the biological effects of the radiation environment at the martian surface and the potential toxic properties of the martian dust. | B3. Crew Health & Performance | B3-2. Simultaneous spectra of solar energetic particles in space and in the surface. | Solar energetic particles at the surface | Determine potential hazards to the crew due to radiation. Validate the atmospheric radiation transport model with orbital and surface measurements with adequate range. SEP intensities can be forecast and detected from the vantage point of space or the Earth. To assess the impact of these events at the surface of Mars, models and tools must account for the details of SEP energy deposition into the atmosphere. Hence successful development of these tools would require simultaneous, accurate measurements of the radiation field both above the atmosphere and on the surface. | Simultaneous orbital and surface measurements of spectra of solar energetic particles before and after atmospheric transmission (The MSL RAD measures the charged particle spectra) | 2. Medium | Mars surface and Mars orbit |  | Radiation detector suite | Previously flown technology | Periodically throughout one martian year (through an entire solar cycle desired)) | 4. IV Late | SEP intensities can be forecast and detected from the vantage point of space or the Earth. To assess the impact of these events at the surface of Mars, models and tools must account for the details of SEP energy deposition into the atmosphere. Hence successful development of these tools would require simultaneous, accurate measurements of the radiation field both above the atmosphere and on the surface.
B3 | B3. Crew Health & Performance. We do not understand in sufficient detail the factors affecting crew health and performance, specifically including the biological effects of the radiation environment at the martian surface and the potential toxic properties of the martian dust. | B3. Crew Health & Performance | B3-3. Spectra of galactic cosmic rays in space. | Galactic cosmic rays in space | Determine potential hazards to the crew due to radiation. Validate the atmospheric radiation transport model with orbital and surface measurements with adequate range. Risks to astronauts from radiation in space have been characterized for decades. Outside the shielding effects of the Earth’s magnetic field and atmosphere, the ever-present flux of Galactic Cosmic Rays (GCRs) poses a long term cancer risk. | Measure spectra of galactic cosmic rays (This can be done near Earth if no magnetospheric interference) Identification of charged particles at the surface from hydrogen to iron and measure particle energies from 10 MeV/nuc to 400 MeV/nuc along with LET measurement during solar min. | 3. Low | NEAR EARTH |  | Radiation detector suite | Previously flown technology | Periodically throughout one martian year (through an entire solar cycle desired)) | 4. IV Late | Measurement of GCR environment on the surface during solar min (assuming RAD will operate only during solar max)
B3 | B3. Crew Health & Performance. We do not understand in sufficient detail the factors affecting crew health and performance, specifically including the biological effects of the radiation environment at the martian surface and the potential toxic properties of the martian dust. | B3. Crew Health & Performance | B3-4. Spectra of galactic cosmic rays on surface. | Galactic cosmic rays on the surface | Determine potential hazards to the crew due to radiation. Validate the atmospheric radiation transport model with orbital and surface measurements with adequate range. Risks to astronauts from radiation in space have been characterized for decades. Outside the shielding effects of the Earth’s magnetic field and atmosphere, the ever-present flux of Galactic Cosmic Rays (GCRs) poses a long term cancer risk. | Measure spectra of galactic cosmic rays after atmospheric transmission including secondary particles from interaction with regolith (The MSL RAD measures the charged particle spectra) Identification of charged particles at the surface from hydrogen to iron and measure particle energies from 10 MeV/nuc to 400 MeV/nuc along with LET measurement during solar min. | 2. Medium | Mars surface |  | Radiation detector suite | Previously flown technology | Periodically throughout one martian year (through an entire solar cycle desired)) | 4. IV Late
B3 | B3. Crew Health & Performance. We do not understand in sufficient detail the factors affecting crew health and performance, specifically including the biological effects of the radiation environment at the martian surface and the potential toxic properties of the martian dust. | B3. Crew Health & Performance | B3-5. Toxicity of dust to crew | Dust physical, chemical and electrical properties | 2C. Investigation: Determine the possible toxic effects of Martian dust on humans. | Assay for chemicals with known toxic effect on humans. Of particular importance are oxidizing species (e.g., CrVI) associated with dust-sized particles. May require a sample returned to Earth as previous assays haven’t been conclusive enough to retire risk. Fully characterize soluble ion distributions, reactions that occur upon humidification and released volatiles from a surface sample and sample of regolith from a depth as large as might be affected by human surface operations. Previous robotic assays (Phoenix) haven’t been conclusive enough to significantly mitigate this risk. Analyze the shapes of martian dust grains with a grain size distribution (1 to 500 microns) sufficient to assess their possible impact on human soft tissue (especially eyes and lungs). | 2. Medium | Sample return |  | Returned sample analysis | Significant new technology needed. | Likely to take many years for the investigations to yield acceptable results. | 4. IV Late | MSR required for dust and granular materials. Subset of DS objectives, so satisfied by that mission.
B3 | B3. Crew Health & Performance. We do not understand in sufficient detail the factors affecting crew health and performance, specifically including the biological effects of the radiation environment at the martian surface and the potential toxic properties of the martian dust. | B3. Crew Health & Performance | B3-6. Radiation protection demo | Demonstrate radiation protection system design(s) | Show that we know how to design systems to protect the crew from radiation. | Demonstrations could be on Earth, in Earth orbit, in Mars orbit, or on the Martian surface | 1. High | Earth or Mars Surface |  | Technology demo | New technology | Single demonstration sufficient | 4. IV Late
B4 | B4. Dust Effects on Engineered Systems. We do not understand the possible adverse effects of martian dust on surface systems. | B4. Dust Effects on Surface Systems | B4-1. Electricity | Electrical properties of the Martian environment | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Electrical: electric field measurement, atmospheric/surface conductivity; long-term (Martian year) atmospheric/surface electrical monitoring | 3. Low | Mars surface |  | Surface electrical measurements | New technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | MSR can address for dust and granular materials. Subset of DS objectives, so satisfied by that mission. | •Past/present habitable/aqueous environments
B4 | B4. Dust Effects on Engineered Systems. We do not understand the possible adverse effects of martian dust on surface systems. | B4. Dust Effects on Surface Systems | B4-1. Electricity | Electrical properties of the Martian environment | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Electrical: electric field measurement, atmospheric/surface conductivity; long-term (Martian year) atmospheric/surface electrical monitoring | 3. Low | Mars surface |  | Surface electrical measurements | New technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | MSR can address for dust and granular materials. Subset of DS objectives, so satisfied by that mission. | •Past/present habitable/aqueous environments
B4 | B4. Dust Effects on Engineered Systems. We do not understand the possible adverse effects of martian dust on surface systems. | B4. Dust Effects on Surface Systems | B4-2. Dust physical, chemical and electrical properties | Electrical properties of the Martian environment | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Determine the electrical conductivity of the ground, measuring at least 10-13 S/m or more, at a resolution DS of 10% of the local ambient value Combine the characterization of atmospheric electricity with surface meteorological and dust measurements to correlate electric forces and their causative meteorological source for more than 1 martian year, both in dust devils and large dust storms (i.e., may be combined with objective 1A. c.) | 2. Medium | Mars surface |  | Surface electrical measurements | New technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late
B4 | B4. Dust Effects on Engineered Systems. We do not understand the possible adverse effects of martian dust on surface systems. | B4. Dust Effects on Surface Systems | B4-2. Dust physical, chemical and electrical properties | Dust physical, chemical and electrical properties | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Chemistry of the dust | 1. High | Mars Surface or Sample return |  | In situ mineralogy | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | MSR can address for dust and granular materials. Subset of DS objectives, so satisfied by that mission. | •Geochemical context for assessing whether life was or is present on Mars
B4 | B4. Dust Effects on Engineered Systems. We do not understand the possible adverse effects of martian dust on surface systems. | B4. Dust Effects on Surface Systems | B4-2. Dust physical, chemical and electrical properties | Dust physical, chemical and electrical properties | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Mineralogy of the dust | 1. High | Mars Surface or Sample return |  | In situ chemistry | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | MSR can address for dust and granular materials. Subset of DS objectives, so satisfied by that mission. | •Geochemical context for assessing whether life was or is present on Mars
B4 | B4. Dust Effects on Engineered Systems. We do not understand the possible adverse effects of martian dust on surface systems. | B4. Dust Effects on Surface Systems | B4-2. Dust physical, chemical and electrical properties | Dust physical, chemical and electrical properties | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Particle shape and size distribution | 1. High | Mars Surface or Sample return |  | Microscopic imaging | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | MSR can address for dust and granular materials. Subset of DS objectives, so satisfied by that mission. | •Nature and evolution of geologic processes affecting the crust
B4 | B4. Dust Effects on Engineered Systems. We do not understand the possible adverse effects of martian dust on surface systems. | B4. Dust Effects on Surface Systems | B4-2. Dust physical, chemical and electrical properties | Dust physical, chemical and electrical properties | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Determine the charge on individual dust grains equal to a value of 10-17 C or greater, for grains with a radius between 1-100 microns | 2. Medium | Sample return |  | Returned sample analysis | Existing technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late
B4 | B4. Dust Effects on Engineered Systems. We do not understand the possible adverse effects of martian dust on surface systems. | B4. Dust Effects on Surface Systems | B4-3. Regolith physical properties and structure | Regolith physical properties and structure | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Layering, heterogeneity & shear strength via purpose-designed trenching | 2. Medium | Mars surface |  | Trenching experiment | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | MSR can address for dust and granular materials. Subset of DS objectives, so satisfied by that mission. | •Nature and evolution of geologic processes affecting the crust
B4 | B4. Dust Effects on Engineered Systems. We do not understand the possible adverse effects of martian dust on surface systems. | B4. Dust Effects on Surface Systems | B4-3. Regolith physical properties and structure | Regolith composition | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Chemistry of the regolith | 2. Medium | Mars Surface or Sample return |  | In situ mineralogy | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | MSR can address for dust and granular materials. Subset of DS objectives, so satisfied by that mission. | •Geochemical context for assessing whether life was or is present on Mars
B4 | B4. Dust Effects on Engineered Systems. We do not understand the possible adverse effects of martian dust on surface systems. | B4. Dust Effects on Surface Systems | B4-3. Regolith physical properties and structure | Regolith composition | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Mineralogy of the regolith | 2. Medium | Mars Surface or Sample return |  | In situ chemistry | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | MSR can address for dust and granular materials. Subset of DS objectives, so satisfied by that mission. | •Geochemical context for assessing whether life was or is present on Mars
B4 | B4. Dust Effects on Engineered Systems. We do not understand the possible adverse effects of martian dust on surface systems. | B4. Dust Effects on Surface Systems | B4-3. Regolith physical properties and structure | Regolith physical properties and structure | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Particle shape and size distribution | 2. Medium | Mars Surface or Sample return |  | Microscopic imaging | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | MSR can address for dust and granular materials. Subset of DS objectives, so satisfied by that mission. | •Nature and evolution of geologic processes affecting the crust
B4 | B4. Dust Effects on Engineered Systems. We do not understand the possible adverse effects of martian dust on surface systems. | B4. Dust Effects on Surface Systems | B4-4. Dust mitigation demo | Demonstrate systems that survive dust or process to mitigate the effect of dust. | Systems must operate in the dusty martian environment | Demonstration could be on Earth or on the Martian surface | 3. Low | Earth or Mars Surface |  | Technology demo | New technology | Single demonstration sufficient | 4. IV Late | MSR partially addresses. Might be fully addressable with minor modifications to MSR systems.
B5 | B5. Forward Contamination to Mars. We are not able to predict with sufficient confidence the potential consequences of the delivery and subsequent dispersal of a large bioload associated with a future human mission to the martian surface. | B5. Forward Contamination to Mars. | B5-1. Identify and map special regions | Orbital measurements for signs of recent water activity Orbital and lander measurements for presence of ground ice. | Do not know whether there are locations (special regions) at or near the surface that are hospitable to terrestrial life, and if so where those locations are | Orbital measurements for signs of recent water activity Orbital and lander measurements for presence of ground ice. | 1. High | Mars surface and Mars orbit |  | Imaging radar Drilling, sample retrieval, and quantitative analysis from previous slide Neutron and gamma ray spectroscopy to measure H in 2 depth ranges (to 50 cm, to 10 cm) | Some instruments previously flown (TRL 8-9). Others at TRL 6 or above | Sufficient to map potential landing zones | 4. IV Late | MSR preparation likely to address.
B5 | B5. Forward Contamination to Mars. We are not able to predict with sufficient confidence the potential consequences of the delivery and subsequent dispersal of a large bioload associated with a future human mission to the martian surface. | B5. Forward Contamination to Mars. | B5-2. Model induced special regions | Develop criteria to identify special regions and use orbiter observations to map exclusion zones for early human missions | Do not know the extent to which human activities would create artificial special regions, contaminated with terrestrial organisms and what the broader impact of such regions would be. | Orbital measurements for signs of recent water activity Orbital and lander measurements for presence of ground ice. | 3. Low | Mars surface and Mars orbit |  | Earth based investigations | N/A | N/A | 4. IV Late | MSR preparation likely to address.
B5 | B5. Forward Contamination to Mars. We are not able to predict with sufficient confidence the potential consequences of the delivery and subsequent dispersal of a large bioload associated with a future human mission to the martian surface. | B5. Forward Contamination to Mars. | B5-3. Microbial survival, Mars conditions | Understand the survivability of terrestrial organisms in Mars conditions. Understand further the habitability of Mars for Terrestrial Microbiota | Do not know the extent to which terrestrial contaminants introduced at a specific, and possibly inhospitable landing site could be dispersed around the planet and introduced into more hospitable sites. | terrestrial work | 2. Medium | Earth |  | Earth based investigations | N/A | N/A | 4. IV Late | MSR preparation likely to address.
B5 | B5. Forward Contamination to Mars. We are not able to predict with sufficient confidence the potential consequences of the delivery and subsequent dispersal of a large bioload associated with a future human mission to the martian surface. | B5. Forward Contamination to Mars. | B5-4. Develop contaminant dispersal model | Develop models to better predict dispersal patterns for contaminants across the planet | Do not know the extent to which terrestrial contaminants introduced at a specific, and possibly inhospitable landing site could be dispersed around the planet and introduced into more hospitable sites. | modeling | 2. Medium | Earth |  | Earth based investigations | N/A | N/A | 4. IV Late | MSR preparation likely to address.
B5 | B5. Forward Contamination to Mars. We are not able to predict with sufficient confidence the potential consequences of the delivery and subsequent dispersal of a large bioload associated with a future human mission to the martian surface. | B5. Forward Contamination to Mars. | B5-5. Forward Contamination Tech demo | Demonstrate methods to control the forward contamination of Mars by terrestrial biology | Required by treaty to meet this requirement | Demonstration could be on Earth or on the Martian surface | 2. Medium | Earth or Mars Surface |  | Technology demo | New technology | Single demonstration sufficient | 4. IV Late
B6 | B6. Atmospheric ISRU. We do not understand in sufficient detail the properties of atmospheric constituents near the surface to determine the adverse effects on ISRU atmospheric processing system life and performance within acceptable risk for human missions. | B6. Atmospheric ISRU. | B6-1. Dust physical, chemical and electrical properties | Dust physical, chemical and electrical properties | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Particle shape and size distribution | 1. High | Mars Surface or Sample return |  | Returned sample analysis | Existing technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | MSR required for dust and granular materials. Subset of DS objectives, so satisfied by that mission.
B6 | B6. Atmospheric ISRU. We do not understand in sufficient detail the properties of atmospheric constituents near the surface to determine the adverse effects on ISRU atmospheric processing system life and performance within acceptable risk for human missions. | B6. Atmospheric ISRU. | B6-2. Dust column abundances | Dust distribution in the atmosphere | Provide sufficient knowledge of dust and regolith to design systems that will work properly and survive in the martian environment. | Column abundance and size-frequency distribution, resolved at less than scale height | 3. Low | Mars surface |  | Upward looking LIDAR Pancam with sun tracking filters upward looking IR sounder | Previously flown technology | for multiple Martian years. | 4. IV Late | See B1-2 (row 18) This needs simultaneous orbital dust observations (A1-2, row 4) and probably Dust Climatology (B1-1, row 15)
B6 | B6. Atmospheric ISRU. We do not understand in sufficient detail the properties of atmospheric constituents near the surface to determine the adverse effects on ISRU atmospheric processing system life and performance within acceptable risk for human missions. | B6. Atmospheric ISRU. | B6-3. Trace gas abundances | Atmospheric chemistry | Provide sufficient knowledge of atmospheric chemistry to design systems that will work properly and survive in the martian environment. | Trace gas abundances | 3. Low | Mars Orbit |  | very high resolution solar occultation mid and near IR spectroscopy, Surface TDL (tunable diode laser) for specific gases of concern | Instrument in development for TGO. Similar instruments flown in earth orbit. TDL on MSL | 1 Mars Year ? | 4. IV Late
B7 | B7. Landing Site and Hazards. We do not yet know of a site on Mars that is certified to be safe for human landing, and for which we understand the type and location of hazards that could affect the ability to safely carry out mobile surface operations. | B7. Landing Site and Hazards. | B7-1. Regolith physical properties and structure | Regolith physical properties and structure | 1. Provide sufficient knowledge of the regolith so that the blast ejecta effects caused by terminal descent engines can be adequately modeled and used in the design of the landing system. 2. Certify landing site is safe to land. | Surface bearing strength; Presence of significant heterogeneities or subsurface features of layering; An index of shear strength | 2. Medium | Mars surface |  | Trenching experiment | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | Might be fully addressable with MSL rover. | •Volatile and dust cycling between the atmosphere and the surface •Present cycling of water •Past/potentially habitable environments •Polar climate (icy sites) •Nature and evolution of geologic processes affecting the crust
B7 | B7. Landing Site and Hazards. We do not yet know of a site on Mars that is certified to be safe for human landing, and for which we understand the type and location of hazards that could affect the ability to safely carry out mobile surface operations. | B7. Landing Site and Hazards. | B7-1. Regolith physical properties and structure | Regolith physical properties and structure | Provide sufficient knowledge of the regolith so that the blast ejecta effects caused by terminal descent engines can be adequately modeled and used in the design of the landing system. | Gas permeability in the range 1 to 300 Darcy with a factor of three accuracy | 2. Medium | Mars surface |  | Gas Permeability | New technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late |  | •Volatile and dust cycling between the atmosphere and the surface •Present cycling of water •Past/potentially habitable environments •Polar climate (icy sites)
B7 | B7. Landing Site and Hazards. We do not yet know of a site on Mars that is certified to be safe for human landing, and for which we understand the type and location of hazards that could affect the ability to safely carry out mobile surface operations. | B7. Landing Site and Hazards. | B7-1. Regolith physical properties and structure | Regolith composition, ice in regolith | Provide sufficient knowledge of the regolith so that the blast ejecta effects caused by terminal descent engines can be adequately modeled and used in the design of the landing system. | Ice content and composition to within 5% by mass | 2. Medium | Mars Surface or Sample return |  | Thermal evolved gas analysis | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late |  | •Volatile and dust cycling between the atmosphere and the surface •Present cycling of water •Past/potentially habitable environments •Polar climate (icy sites)
B7 | B7. Landing Site and Hazards. We do not yet know of a site on Mars that is certified to be safe for human landing, and for which we understand the type and location of hazards that could affect the ability to safely carry out mobile surface operations. | B7. Landing Site and Hazards. | B7-1. Regolith physical properties and structure | Regolith physical properties and structure | Provide sufficient knowledge of the regolith so that the blast ejecta effects caused by terminal descent engines can be adequately modeled and used in the design of the landing system. | Flow Rate Index test or other standard flow index measurement | 2. Medium | Mars Surface or Sample return |  | Regolith flow | New technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | MSR would require augmentation to do in situ, but can be completed on the returned samples. | •Volatile and dust cycling between the atmosphere and the surface •Present cycling of water •Past/potentially habitable environments •Polar climate (icy sites)
B7 | B7. Landing Site and Hazards. We do not yet know of a site on Mars that is certified to be safe for human landing, and for which we understand the type and location of hazards that could affect the ability to safely carry out mobile surface operations. | B7. Landing Site and Hazards. | B7-1. Regolith physical properties and structure | Regolith physical properties and structure | Provide sufficient knowledge of the regolith so that the blast ejecta effects caused by terminal descent engines can be adequately modeled and used in the design of the landing system. | Particle shape and size distribution | 2. Medium | Mars Surface or Sample return |  | Microscopic imaging | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | MSR can do in situ. | •Volatile and dust cycling between the atmosphere and the surface •Present cycling of water •Past/potentially habitable environments •Polar climate (icy sites)
B7 | B7. Landing Site and Hazards. We do not yet know of a site on Mars that is certified to be safe for human landing, and for which we understand the type and location of hazards that could affect the ability to safely carry out mobile surface operations. | B7. Landing Site and Hazards. | B7-2. Landing site selection | Surface obstacles or hazards (rocks, slopes) | Allow real-time feature recognition during terminal descent to avoid hazards and place new landers relative to previously placed systems or infrastructure. Certify landing site is safe to land. Identify surface hazards to aid in traverse planning | (a) Establish terrain knowledge error to ~10 meters vertical and ~100 meters horizontal within the landing ellipse of each potential landing site; (b) Measure slopes at 1 km, 100 m and 10 m length scales to within 1 degree; (c) Map cliffs, scarps, craters/depressions, rock concentrations and other significant terrain features that could be potential surface hazards (d) High resolution visual and other remote data types (sufficient to design and then train landing guidance systems); (e) Identify specific terrain features to be used for navigation and establish terrain knowledge error to ~10 meters vertical and ~50 meters horizontal within the landing ellipse of each potential landing site | 2. Medium | Mars Orbit |  | High resolution orbital imagery | Previously flown technology | Sufficient to map potential landing zones | 4. IV Late |  | •Connections with human exploration •Past/potentially habitable environments •Nature and evolution of geologic processes affecting the crust
B7 | B7. Landing Site and Hazards. We do not yet know of a site on Mars that is certified to be safe for human landing, and for which we understand the type and location of hazards that could affect the ability to safely carry out mobile surface operations. | B7. Landing Site and Hazards. | B7-2. Landing site selection | Regolith physical properties and structure | Certify landing site is safe to land. Identify surface hazards to aid in traverse planning | Map thermal inertia sufficient to identify dust accumulations that would cause either roving hazards. [It is estimated that a knowledge of dust accumulations on the order of 1 km2 (approximately an order of magnitude better resolution than TES)] | 2. Medium | Mars Orbit |  | Thermal inertia | Previously flown technology | Sufficient to map potential landing zones | 4. IV Late |  | •Past/potentially habitable environments •Nature and evolution of geologic processes affecting the crust
B7 | B7. Landing Site and Hazards. We do not yet know of a site on Mars that is certified to be safe for human landing, and for which we understand the type and location of hazards that could affect the ability to safely carry out mobile surface operations. | B7. Landing Site and Hazards. | B7-2. Landing site selection | Regolith composition | Certify landing site is safe to land. | Bearing strength via composition (in situ mineralogy) | 2. Medium | Mars surface |  | In situ mineralogy | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | Might be fully addressable with MSL rover. | •Past/potentially habitable environments •Nature and evolution of geologic processes affecting the crust
B7 | B7. Landing Site and Hazards. We do not yet know of a site on Mars that is certified to be safe for human landing, and for which we understand the type and location of hazards that could affect the ability to safely carry out mobile surface operations. | B7. Landing Site and Hazards. | B7-3. Trafficability | Regolith physical properties and structure | Determine trafficability characteristics of surface material to aid in the design of surface rovers. | Determine traction/cohesion in martian soil/regolith (with emphasis on trafficability hazards, such as dust pockets and dunes) throughout planned landing sites, including (a) vertical variation in in-situ soil density within the upper 30 cm for rocky areas, on dust dunes, and in dust pockets to within 0.1 g/cm3, (b) variation in in-situ internal angle of friction of soil for dust dunes and dust pockets to within 1 degree, and (c) soil cohesion for rocky areas, dust dunes and in dust pockets to within 0.1 kN/m2 | 3. Low | Mars surface |  |  | New technology | Single experiment may address, but enhanced by multiple measurements. | 4. IV Late | Not sure these measurements are feasible | •Nature and evolution of geologic processes affecting the crust
B7 | B7. Landing Site and Hazards. We do not yet know of a site on Mars that is certified to be safe for human landing, and for which we understand the type and location of hazards that could affect the ability to safely carry out mobile surface operations. | B7. Landing Site and Hazards. | B7-4. Auto rover tech demo | Demonstrate autonomous rover operations and advanced surface mobility | Enable autonomous rovers working to support astronaut operations | Demonstration could be on Earth or on the Martian surface | 3. Low | Earth or Mars Surface |  | Technology demo | New technology | Single demonstration sufficient | 4. IV Late | MSR could address
B7 | B7. Landing Site and Hazards. We do not yet know of a site on Mars that is certified to be safe for human landing, and for which we understand the type and location of hazards that could affect the ability to safely carry out mobile surface operations. | B7. Landing Site and Hazards. | B7-5. Env exposure tech demo | Demonstrate the survival of materials, mechanisms, and components exposed to the Mars environment | Systems must survive the Martian surface environment for the duration of the missions they support. | Demonstration should be on the Martian surface | 1. High | Mars surface |  | Technology demo | New technology | Single demonstration sufficient | 4. IV Late | MSR could test some of this.
B7 | B7. Landing Site and Hazards. We do not yet know of a site on Mars that is certified to be safe for human landing, and for which we understand the type and location of hazards that could affect the ability to safely carry out mobile surface operations. | B7. Landing Site and Hazards. | B7-6. Sample handling tech demo | Demonstrate Sample acquisition, handling, and caching | Required to return samples for scientific analysis | Demonstration could be on Earth or on the Martian surface | 3. Low | Earth or Mars Surface |  | Technology demo | New technology | Single demonstration sufficient | 4. IV Late | MSR could address
B8 | B8. Technology: Mars Surface. In addition to the specific challenges listed above, we do not have the required technology available to: (1) land human-scale payloads on the martian surface; (2) sustain humans on the surface of Mars; (3) enable human mobility and exploration of the Mars surface environment; all within acceptable risk. | B8. Technology: Mars Surface. | B8-1. Fission power tech demo | Demonstrate Fission based surface power | High power levels needed to support human surface operations and ISRU. | Demonstration could be on Earth | 1. High | Earth |  | Technology demo | New technology | Single demonstration sufficient | 4. IV Late
C1 | C1. Phobos/Deimos surface science. We do not have enough understanding of the geological, compositional, and geophysical properties of Phobos and Deimos in order to design focused human-based scientific investigations and engineering activities with precise objectives like those now possible for the Martian surface. | C1. Phobos/Deimos surface science. | C1-1. Surface composition | Mineralogical & chemical composition | determine which areas of Phobos/Deimos to explore | Elemental / chemical composition; spatial distribution of major geologic units; ISRU potential | 1. High | Phobos and/or Deimos rendezvous and lander |  | Spectrometers (visible, near-Infrared, thermal), Imaging cameras, APXS, XRF, Mossbauer, mass spec, neutron and gamma ray spectrometers, etc. | Previously flown or moderate TRL. | Sufficient to map potential landing zones and interact with materials at landing sites | 2. IV- P/D |  | Related to the origins and the evolution of small bodies. Of interest to SBAG science objectives see SBAG roadmap.
C2 | C2. Phobos/Deimos surface Ops. We do not know how to perform close proximity and surface interactions (docking/anchoring/mobility) in the conditions present near/at the surface of the martian satellites (low gravity/loose regolith/significant temperature variations/etc.) in order to implement human-based scientific investigations and engineering activities. | C2. Phobos/Deimos surface Ops. | C2-1. P/D electric and plasma environments | In space radiation environment at Phobos and Deimos | Determine potential hazards to the crew due to radiation. | Total dose from solar particles, galactic cosmic rays and secondaries | 3. Low | Phobos and/or Deimos rendezvous |  | Radiation detector suite | Some expertise from CRATER on LRO, needs some additional development | Periodically throughout one martian year (through an entire solar cycle desired)) | 2. IV- P/D | •Radiation. Require(?) better understanding of interaction with Phobos/Deimos for shielding/secondary effects. The SKG relates to tissue equivalent response, not to basic measurement of GCR and SEPs.
C2 | C2. Phobos/Deimos surface Ops. We do not know how to perform close proximity and surface interactions (docking/anchoring/mobility) in the conditions present near/at the surface of the martian satellites (low gravity/loose regolith/significant temperature variations/etc.) in order to implement human-based scientific investigations and engineering activities. | C2. Phobos/Deimos surface Ops. | C2-1. P/D electric and plasma environments | Surface and subsurface radiation environment at Phobos and Deimos | Determine potential hazards to the crew due to radiation. | Total dose from solar particles, galactic cosmic rays and secondaries | 3. Low | Phobos and/or Deimos rendezvous |  | Radiation detector suite | Some expertise from CRATER on LRO, needs some additional development | Periodically throughout one martian year (through an entire solar cycle desired)) | 2. IV- P/D | •Radiation. Require(?) better understanding of interaction with Phobos/Deimos for shielding/secondary effects. The SKG relates to tissue equivalent response, not to basic measurement of GCR and SEPs.
C2 | C2. Phobos/Deimos surface Ops. We do not know how to perform close proximity and surface interactions (docking/anchoring/mobility) in the conditions present near/at the surface of the martian satellites (low gravity/loose regolith/significant temperature variations/etc.) in order to implement human-based scientific investigations and engineering activities. | C2. Phobos/Deimos surface Ops. | C2-1. P/D electric and plasma environments | Electrostatic charging & plasma fields | Determine potential impacts on spacecraft systems | Electric fields in proximity to surface, plasma emanating from surface | 3. Low | Phobos and/or Deimos rendezvous |  | Langmuir Probe | Previously flown on Rosetta | In close proximity to Phobos/Deimos for extended periods of time. Need to measure environment during quiescent and active solar periods. | 2. IV- P/D | •Electrostatics. Electrostatic charging and plasma environment influences engineering of surface elements and EVA equipment designs. | Related to the environment around small bodies and the dynamics involved in regolith levitation and migration. Of interest to SBAG science objectives see SBAG roadmap.
C2 | C2. Phobos/Deimos surface Ops. We do not know how to perform close proximity and surface interactions (docking/anchoring/mobility) in the conditions present near/at the surface of the martian satellites (low gravity/loose regolith/significant temperature variations/etc.) in order to implement human-based scientific investigations and engineering activities. | C2. Phobos/Deimos surface Ops. | C2-2. P/D Gravitational field | Gravitational fields of Phobos and Deimos | Needed for planning operations near Phobos and Deimos | Spherical harmonic terms of moons’ gravitational fields | 2. Medium | Phobos and/or Deimos rendezvous |  | Radioscience tracking | Previously flown technology | Sufficient to adequately map Phobos/Deimos gravity field to high degree and order (4 and higher) for close proximity operations | 2. IV- P/D | Gravity. Gravitational field measurements recommended for planning proximity operations, including station keeping modes. | Related to the internal structure of Phobos/Deimos. Of interest to SBAG science objectives see SBAG roadmap.
C2 | C2. Phobos/Deimos surface Ops. We do not know how to perform close proximity and surface interactions (docking/anchoring/mobility) in the conditions present near/at the surface of the martian satellites (low gravity/loose regolith/significant temperature variations/etc.) in order to implement human-based scientific investigations and engineering activities. | C2. Phobos/Deimos surface Ops. | C2-3. P/D regolith properties | Composition of Phobos and Deimos | Determine effects on mechanical systems | Elemental / chemical composition; spatial distribution of major geologic units | 1. High | Phobos and/or Deimos rendezvous and lander |  | Spectrometers (visible, near-Infrared, thermal), Imaging cameras, APXS, XRF, Mossbauer, mass spec, neutron and gamma ray spectrometers, etc. | Previously flown or moderate TRL. | Sufficient to map potential landing zones and interact with materials at landing sites | 2. IV- P/D | •Mineralogy et al. Mineralogy/chemistry needed to support productive science operations; may also influence operations planning | Related to the origins of Phobos/Deimos and whether they contain volatile rich materials. Of interest to SBAG science objectives see SBAG roadmap.
C2 | C2. Phobos/Deimos surface Ops. We do not know how to perform close proximity and surface interactions (docking/anchoring/mobility) in the conditions present near/at the surface of the martian satellites (low gravity/loose regolith/significant temperature variations/etc.) in order to implement human-based scientific investigations and engineering activities. | C2. Phobos/Deimos surface Ops. | C2-3. P/D regolith properties | Phobos/Deimos Regolith mechanical & geotechnical properties | Determine effects on mechanical systems for anchoring and mobility | Size-frequency distribution; density, compressibility, adhesion; spatial variation in thickness/properties | 1. High | Phobos and/or Deimos rendezvous and lander |  | Ground penetrating radar, micro-imagers, surface interaction experiments, penetrators, thermal probes, particle/dust static surface collectors, mechanical arm, rovers, hoppers, floppers, etc. | Some previous flight heritage, Moderate TRL. | Requires direct interaction at landing site(s) with sufficient duration to characterize surface and sub-surface material properties | 2. IV- P/D | Regolith. Regolith contact measurement and mapping needed for ops planning and surface interaction considerations | Related to the regolith conditions of Phobos/Deimos and pertains to the surface evolution of small bodies. Of interest to SBAG science objectives see SBAG roadmap.
C2 | C2. Phobos/Deimos surface Ops. We do not know how to perform close proximity and surface interactions (docking/anchoring/mobility) in the conditions present near/at the surface of the martian satellites (low gravity/loose regolith/significant temperature variations/etc.) in order to implement human-based scientific investigations and engineering activities. | C2. Phobos/Deimos surface Ops. | C2-3. P/D regolith properties | P/D Particulate physical, chemical and electrical properties | Determine the possible detrimental effects of Phobos/Deimos particulates on science operations and engineering equipment. | Cohesion, adhesion and their interaction of particulates to precursor spacecraft and science packages and/or rovers. | 1. High | Phobos and/or Deimos rendezvous and lander |  | Ground penetrating radar, micro-imagers, surface interaction experiments, penetrators, thermal probes, particle/dust static surface collectors, mechanical arm, rovers, hoppers, floppers, etc. | Some previous flight experience, but some new technology needed. | Requires direct interaction at landing site(s) with sufficient duration to characterize surface and sub-surface material interactions with equipment packages | 2. IV- P/D |  | Related to the regolith conditions of Phobos/Deimos and pertains to the surface evolution of small bodies. Of interest to SBAG science objectives see SBAG roadmap.
C2 | C2. Phobos/Deimos surface Ops. We do not know how to perform close proximity and surface interactions (docking/anchoring/mobility) in the conditions present near/at the surface of the martian satellites (low gravity/loose regolith/significant temperature variations/etc.) in order to implement human-based scientific investigations and engineering activities. | C2. Phobos/Deimos surface Ops. | C2-4. P/D thermal environment | Phobos/Deimos Thermal environment | Determine effects on mechanical systems | Temperature variation diurnally, with depth | 3. Low | Phobos and/or Deimos rendezvous and lander |  | thermal imagers, cameras, temperature probes, rovers, floppers, hoppers | Moderate TRL with some flight experience | Sufficient to characterize the thermal properties of the surface over Phobos/Deimos diurnal timescales | 2. IV- P/D | •Thermal. Thermal environmental conditions vary significantly over diurnal time scales and regolith depth. Data inform adequate engineering of surface elements, including EVA equipment designs. | Related to the regolith conditions of Phobos/Deimos and pertains to the thermal environment on small bodies. Of interest to SBAG science objectives see SBAG roadmap.
C3 | C3. Technology: Phobos/Deimos. We do not have the technologies required to perform close proximity and surface interactions in the conditions present near/at the surface of the martian satellites in order to safely and efficiently implement human-based scientific investigations and engineering activities. | C3. Technology: Phobos/Deimos | C3-1. Anchoring and surface mobility systems | Demo of anchoring and mobility techniques | Need to access sites on Phobos/Deimos of scientific and engineering interest | Measure regolith and geotechnical properties under low-gravity conditions at an uncooperative target surface | 1. High | Phobos and/or Deimos rendezvous and lander |  | Technology demo | New technology | Surface Interaction at Phobos/Deimos at representative site(s( of interest | 2. IV- P/D | Relevant for all aspects of science and engineering. Of interest for ISRU technologies as well. Overlaps with technology development for exploration of asteroids. | Relevant to SBAG Roadmap objectives for technology advancements in several areas of small body exploration. See the SBAG roadmap.
D1 | D1. Resources. We do not fully understand if resources (including water and other useful material) on Mars or its moons occurs in a form that could change the high-level architecture of a sustained human presence on the surface. | D1. Water Resources | D1-1. Cryo storage demo | Demonstrate cryogenic propellant storage system design(s) | Since cryogenic propellants have higher ISP than other propellant, these are the one we would prefer to use, but to do so on long missions requires cryogenic propellant storage. Also support ISRU propellants. | Demonstration could be on Earth or in Earth orbit | 2. Medium | Earth |  | Earth based investigations | New technology | Single demonstration sufficient | 4. IV Late
D1 | D1. Resources. We do not fully understand if resources (including water and other useful material) on Mars or its moons occurs in a form that could change the high-level architecture of a sustained human presence on the surface. | D1. Water Resources | D1-2. Water ISRU demo | Demonstrate extraction and use of water from surface materials. | ISRU has the potential to greatly reduce the materials that need to be transported to the Martian surface. | Demonstration could be on Earth or on the Martian surface | 2. Medium | Earth or Mars Surface |  | Technology demo | New technology | Single demonstration sufficient | 5. IV+
D1 | D1. Resources. We do not adequately understand if resources (most importantly water, but also other useful material) on Mars or its moons occurs in a location/form that could influence the high-level architecture of the missions/infrastructure associated with a sustained human presence in the martian system. | D1. Water Resources | D1-3. Hydrated mineral compositions | Hydrated mineral compositions | Determine the properties of hydrated minerals to allow for the design of systems to extract water as a resource. | "Mineralogy including minor components. Detect mineral phases present at the 1% level. Achieve ±2% accuracy in volume % for phases present at 10% level, averaged over all measurements. Elemental and mineral chemistry including minor components. Detect elements present at the 0.1% level. Achieve ±0.2 weight % accuracy for elements present at 1% level, averaged over all measurements." Energy needed to evolve water | 1. High | Sample return |  | In situ mineralogy In situ chemistry | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 5. IV+ | Needs orbital High Resolution Spectroscopy. Sample return rover could satisfy landed in situ objectives. Returned samples address minor components.
D1 | D1. Resources. We do not adequately understand if resources (most importantly water, but also other useful material) on Mars or its moons occurs in a location/form that could influence the high-level architecture of the missions/infrastructure associated with a sustained human presence in the martian system. | D1. Water Resources | D1-4. Hydrated mineral occurrences | Hydrated mineral occurrences | Determine the properties of hydrated minerals to allow for the design of systems to extract water as a resource. | Occurrences and internal structure of deposits at ≤5 m/pixel, goal 2 m/pixel. Spectral range 0.4-2.5 µm, goal 0.4-3.1 µm. Spectral sampling adequate to distinguish major mineral classes including olivine, pyroxene, ferric minerals, phyllosilicates, and hydrated sulfates, silica, and carbonate. | 1. High | Mars Orbit |  | High resolution orbital spectroscopy | Previously flown technology | Sufficient to map potential landing zones | 5. IV+ | Needs orbital High Resolution Spectroscopy and high resolution imaging. Sample return rover could satisfy landed in situ objectives.
D1 | D1. Resources. We do not adequately understand if resources (most importantly water, but also other useful material) on Mars or its moons occurs in a location/form that could influence the high-level architecture of the missions/infrastructure associated with a sustained human presence in the martian system. | D1. Water Resources | D1-5. Shallow water ice composition and properties | Shallow water ice composition | Determine the properties of shallow water ice to allow for the design of systems to extract water as a resource. | Evolved volatiles Energy requirements for extraction and other phases present Mechanical properties | 2. Medium | Mars surface |  | Differential scanning calorimetry Thermogravimetric analysis Evolved gas analysis Gas chromatography Grinder like MER accompanied by contact instrumentation Drill like MSL accompanied by sample preparation and analytical laboratory Scoop to characterize unconsolidated material | Previously flown technology | Single experiment may address, but enhanced by multiple measurements. | 5. IV+
D1 | D1. Resources. We do not adequately understand if resources (most importantly water, but also other useful material) on Mars or its moons occurs in a location/form that could influence the high-level architecture of the missions/infrastructure associated with a sustained human presence in the martian system. | D1. Water Resources | D1-6. Shallow water ice occurrences | Shallow water ice distribution | Determine the distribution of shallow water ice to assess the feasibility of extracting resources at various locations on Mars. | Abundance of ice within upper meter and variation with depth | 2. Medium | Mars surface and Mars orbit |  | Imaging radar Drilling, sample retrieval, and quantitative analysis from previous slide Neutron and gamma ray spectroscopy to measure H in 2 depth ranges (to 50 cm, to 10 cm) | Some instruments previously flown (TRL 8-9). Others at TRL 6 or above | Sufficient to map potential landing zones | 5. IV+
D2 | D2. Technology: In addition to the specific challenges listed in B-8, we do not have the required technology available to: (1) repeatedly land human-scale payloads on the martian surface; (2) sustain humans on the surface of Mars for long durations (multiple martian years); (3) reduce logistical support through the use of a wide range of in situ resources; all within acceptable risk. | D2. Technology: Sustained Presence | D2-1. Repeatedly land | Repeatedly land human-scale payloads on the martian surface |  |  | 1. High | Earth |  |  |  |  | 5. IV+
D2 | D2. Technology: In addition to the specific challenges listed in B-8, we do not have the required technology available to: (1) repeatedly land human-scale payloads on the martian surface; (2) sustain humans on the surface of Mars for long durations (multiple martian years); (3) reduce logistical support through the use of a wide range of in situ resources; all within acceptable risk. | D2. Technology: Sustained Presence | D2-2. Sustain humans | Sustain humans on the surface of Mars for long durations (multiple years) |  |  | 1. High | Earth |  |  |  |  | 5. IV+
D2 | D2. Technology: In addition to the specific challenges listed in B-8, we do not have the required technology available to: (1) repeatedly land human-scale payloads on the martian surface; (2) sustain humans on the surface of Mars for long durations (multiple martian years); (3) reduce logistical support through the use of a wide range of in situ resources; all within acceptable risk. | D2. Technology: Sustained Presence | D2-3. Reduce logistical support | Reduce logistical support through the use of a wide range of in situ resources |  |  | 1. High | Earth |  |  |  |  | 5. IV+
Flight
Ground
Technology
Note on G6: Charles Budney: Can you add a short description?
Note on E18: Charles Budney: Can the local weather items be combined? Or clearly separated into orbital and landed measurements?
Note on F18: Charles Budney: Can the local weather items be combined? Or clearly separated into orbital and landed measurements?